Knaresborough Neighbourhood Development Working Group

Minutes of meeting held on 26th November

Council Chamber, Knaresborough House, High Street Knaresborough

In attendance

David Goode (chair), David Gluck, Jill Laecy, Mavis Clemmitt, Andy Grinter, John Richards. Andrew and Christine Willoughby, Dave Bulmer, Emma Walsh, Wendy Sanderson, Bryan Robertson, Vigne Kovacek , Elizabeth Collins

Apologies - Bill Rigby, Maggie Richards, Lynda Powell

- Mins from last meeting held on 26th October approved

- Updated Project Plan was tabled. Updates showing progress will be tabled at regular intervals.

- Structure of final documents/s – David Gluck highlighted that there are now 100's of plans now completed. Action - David was asked to provide some examples of recently completed plans. David talked to the team through the basic design principles.

Core set of chapters

Statement of facts

Vision

Set of clear objectives – something that is achievable

How is the objectives going to be achieved

What policies support these objectives

What evidence exists that support these policies.

Action - David to provide supporting document to be sent with these minutes.

- Consultancy Spreadsheet – Summary report now completed to reflect combined results of both on line and hard copy forms. Combined results table is only one we will use going forward.

- Green Space Review/Assessment Framework. Small working group to be set up to update the information collected to date, priorities areas and put into the latest format that aligns with NDP/Local Plan criteria.

The discussion developed into the need for a number of working groups who will develop objectives, policies and collect evidence base for final document.

The following working groups were agreed and members of groups are as follows.

Green Space – David Goode (lead), Wendy Sanderson, Bill Rigby

Character Area Appraisals – Andrew Willoughby (lead), Christine Willoughby, Mavis Clemmitt, Bryan Robertson, Shan Rigby

Town Centre Economy – Emma Walsh (lead), Andy Grinter, Vigne Kovacek, Elizabeth Collins, David Bulmer

Countryside – Bill Rigby (lead), Adrew Willoughby, Jill Laecy

Action - Member of each working group to try to get other people to join their teams

Action – each group to have an outline plan of their work program to present at the next meeting on the 7th Jan 2016

- Working with Renaissance Knaresborough/Issues Workshop – workshop has been set up with aim of getting both organizations to work more effectively together. Taking place on evening 16th December, Knaresborough House. Action - NDP working group members are invited.

- NDP WEB page http://www.knaresboroughtowncouncil.gov.uk/Core/Knaresborough-TC/Pages/Neighbourhood_Development_Plan_2.aspx. This has now been redisigned to support the next phase of the NDP program.

- Communication with stakeholders – Community engagement is a key measure of success when the NDP plan goes for review by HBC and the Planning Inspector. Extensive evidence is needed to show this has taken place. Action – David G is starting to compile a spreadsheet of contact. Andy Grinter to send David a copy of the spreadsheet reviewed at the meeting.

- AOB – various events were promoted.

- Next meeting 7th Jan 2016, Council Chamber, start time 7:30