Knaresborough Neighbourhood Development Working Group

Minutes of meeting held on 7th Jan 2016

Council Chamber, Knaresborough House, High Street Knaresborough

In attendance

David Goode (chair), David Gluck, Jill Laecy, Mavis Clemmitt, Andy Grinter,  Andrew and Christine Willoughby, Dave Bulmer, Emma Walsh, Bryan Robertson, Vigne Kovacek ,

Apologies - Bill Rigby, Maggie Richards, Lynda Powell, Elizabeth Collins, Wendy Sanderson

- Mins from last meeting held on 26th Nov approved

- Updated Project Plan was tabled. Request was made to provide updates with Agenda mailing.

- Work-stream updates

  - Green Spaces – David Goode Initial analysis of original list undertaken. Group fining it difficult to reduce list to more manageable length. Plan is to visit many of  the sites over  the next couple of weeks. David Gluck will provide challenge to next version of list.

  - Character Areas – Andrew Willoughby starting to work out different areas. Identifying locations that have clear identities. Aiming to put boundaries around each area. Andrew asked David Gluck to provide a template for Character areas. Action complete information shared with all members.

  - Town Center – Emma Walsh Just starting, initial discussions going on via e mail, Andy G has already done some work which is well documented, looking to collect data to improve evidence base, contacting more local business owners.

  - Countryside – Bill Rigby not yet started but Bill looking to get the team together shortly. Document will highlight land use designations, historic features, and key views across the town. Issues related to the protection of SSSI will be identified and policies to address these will be developed.

  - Each group needs to collect good photographic records, potential for creating mood board

  - Christine will provide group with copy Conservation Area Appraisal document.

  - Need to ensure policies to protect Abbey Road and Waterside are inclded in our final document

- Housing – waiting for HBC Local Plan call for sites to be published. Given latest flooding issues need to cover this in our final doc. Need workshop to discuss issues such as location, need, character.

- Ask planning to attend a future meeting – present how local plan is progressing. Also need to get Economic Development team at HBC involved.

- Need to build up publicity for our work. David looking to kick off production of a newsletter.  Investigate potential to get display in an empty shop. (Andrew Porter).

- Next meeting 2nd February 2016, Council Chamber, start time 7:30