Knaresborough Neighbourhood Development Working Group

Minutes of meeting held on 1st March 2016

Council Chamber, Knaresborough House, High Street Knaresborough

In attendance

David Goode (chair), David Gluck, Bill Rigby, Helen Lyons, Andy Grinter,  Dave Bulmer, Emma Walsh, Bryan Robertson, Elizabeth Collins,Wendy Sanderson, Mavis Clemmitt , Shan Oakes

Apologies -  Andrew and Christine Willoughby, Gill Lacey, Maggie Richards,  Vigne Kovacek

Visitors – Rachel Hutton Senior Planning Officer HBC, Gayle Black MCP  representing Manse Farm development team.

- Mins from last meeting held on 2nd Feb approved

- Updated Project Plan was tabled. It was highlighted that the next key date is the 31st March when we will have a first pass of our NDP document completed. The project has slipped about a month from the original plan. Aim is to try and avoid further slippages.

- Rachel Hutton provided an excellent overview of current status of the development of the District Local Plan. Presentation attached with distribution of minutes. Slides have notes which summaries the key points Rachel made in the presentation. Rachel highlighted the evidence base that HBC is compiling in support of the Local Plan development highlighting that some of this material could be used within the Knaresborough NDP plan avoiding duplication of effort. Rachel offered help to working group members. Both Bill R and David Go have already done some work with Rachel. Rachel is happy to attend future meeting on an invitation basis as long as we give prior notice of topic area we would like here to cover. One key point made in presentation was that it is not a given that HBC will allocate a housing number to the Knaresborough area. HBC are considering two option either allocate a number or let market forces set the number. This further highlights the need for a robust housing section to our NDP plan.

- Work-stream updates

  - Green Spaces –  Continuing to work on spreadsheet of sites

  - Character Areas –  Majority of areas now documented. Thanks with expressed by the working group for the excellent work this team is doing lead by Andrew.

  - Town Centre –  Team finding this area challenging. David Gluck is going to spend further time with Emma overcome any difficulties being faced. Team adding a section on Dementia Friendly Town.

  - Countryside –  Bill R presented an overview of the current thinking with regards to development of this work area. This now needs to be documented by end of month latest. ( Presentation has too many pictures so too large to mail directly. Please contact Bill if you want a copy.)

  - Housing – Andrew W. has started to do some background planning on this topic. He has contacted David Gluck who has provided guidance as to next steps this team needs to take.

Confirmation on members of this team David Go. Christine, Andrew, David B, Wendy and Helen Lyons. Andrew to set up meeting dates for this team ASAP.

- David Gluck outlined progress on formulating content to go into the main document. He highlighted the goal of getting a first pass of the document done by end of March. He needs further content from working groups ASAP. Where appropriate David Gluck will in addition add standard boiler plate content to the document plus policy intention information either provided by sub groups or in some cases based on his knowledge of our program aims and intentions. David again offered help and support to all the sub teams. Just send him a mail or give him a ring if you need help and guidance.

- David Go. presented NDP program to Knaresborough Rotary 15th Feb went well. Has invites to attend Civic Society and Knaresborough Labour Group meetings. Happy to do others David asked members to identify other groups and pass contact information back to him. Presentation material distributed in an earlier mailing.

- Next meeting Tuesday 12th April 2016, Council Chamber, start time 7:30