Knaresborough Neighbourhood Development Working Group

Minutes of meeting held on 2nd Feb 2016

Council Chamber, Knaresborough House, High Street Knaresborough

In attendance

David Goode (chair), David Gluck, Bill Rigby, Andy Grinter,  Andrew and Christine Willoughby, Dave Bulmer, Emma Walsh, Bryan Robertson, Elizabeth Collins,Wendy Sanderson,

Apologies - Gill Lacey, Maggie Richards, Mavis Clemmitt , Vigne Kovacek

- Mins from last meeting held on 7th Jan approved

- Updated Project Plan was tabled.

- Work-stream updates

  - Green Spaces –  First pass of indroductory words and policy statement complete. Group has visited many of the sites throughout the town and taken pictures. Started reworking spreadsheet.

  - Character Areas –  Lot of work been put in to identify potentially 9 areas. Description for each area currently being documented.

  - Town Centre –  Team has met. Coming up with some new creative ideas. Started to document these. Plan is to share the draft dock with key stake holders in town to get feedback.

  - Countryside –  Team identified two areas North East/South West. Bill and Andrew currently in process of walking the two areas. Will then  start to create document. Will aim to bring in other local groups with intrests in this arae.

  - Housing – following release of site submissions by HBC the concensus of the meeting was that now was time to kick off this sub team. Members David G. Christine, Andrew, David B, Wendy others welcome to join. Andrew will lead this work stream.

ACTION

  - Each sub team was asked to provide first pass of their words by mid Feb to David Gluck.

  - Bill Rigby agreed to give team members access to the Dropbox account he has set up to support NDP program.

David Gluck provided team with document framework which will form the master document template.

Outreach activity –	David meeting with Rachel Hutton HBC Planning  3rd Feb. ( see seperate doc for 			meeting report.)

David presenting NDP program to Knaresborough Rotary 15th Feb.

AOB - Potentail new team member Debbie Howard – Introduced by Emma unable to attend meetings but happy to help with copy writing when team needs the help and support.

- Next meeting 1st March 2016, Council Chamber, start time 7:30