Knaresborough Neighbourhood Development Working Group

Minutes of meeting held on 12th July 2016

Aspin School Knaresborough

In attendance

David Goode (chair), David Gluck, Mavis Clemmitt,  Christine Willoughby,Wendy Sanderson, Emma Walsh, Gillian Lacey. Shan Oakes

Apologies

Bryan Robertson, Elizabeth Collins,  Bill Rigby,  Andy Grinter, Andrew Willoughby

Mins of previous meeting agreed.

Revised project plan reviewed for overall program plus new plan specific for document development with aim of having a document fit for public consultation by mid October 16.

Copies of Vision and Objectives handed out. Group member asked to included the principles outlined in the document within specific section of document.

Meeting reviews.

Chair has presented NDP program to local Labour party members and Chamber of trade.

Plus had a meeting with Gary Bell Chief Planner HBC – see separate meeting report.

Links to example of recent completed NDP documents was reviewed in meeting. David Gluck has supported these programs. Leeds Council's feed back on one of plans one of the best they had seen.

Emma Walsh has provided an initial paper on Green issues for consideration for inclusion as section in NDP document.

Bill has committed to provide first pass of countryside overview/issues doc by end of week – action was completed.

Policy development. David Gluck will take lead on these. Gave example of Town Centre policies section.

Templates.

David Gluck provided list of Heritage Assets in the town. It was pointed out that this needed some editing as some on list were not specific to Knaresborough.

Green Spaces spreadsheet Wendy Sanderson finishing this – Document has now been submitted.

Need to start to complete spreadsheet for non designate community facilities.

Community/Statuary authority engagement. David Gluck is going to set up these meetings.

AOB

Discussion on need for document designer.

Next meeting 18th August 7:30 pm   Council Chamber, Knaresborough House Knaresborough, HG5 0HW