Knaresborough Neighbourhood Development Working Group

Minutes of meeting held on 6th Dec 7:30 pm   Council Committee Room, Knaresborough House Knaresborough, HG5 0HW

In attendance

David Goode (chair), David Gluck, Bryan Robinson,   Christine Willoughby, Andrew Willoughby,  Bill Rigby, Emma Walsh,  Shaun Oaks

Apologies

Mavis Clemmitt, Wendy Sanderson,

Mins of previous meeting agreed.

DG – informed team that Elizabeth Collins has sent in her resignation from the Working Group and requested to be taken off the distribution list. The working group expressed thanks for Elizabeth's contribution to the NDP program and would welcome her back if she chose to rejoin the team.

Statuary authorities pre consultation

DG confirmed that the pre - consultancy document had been sent to Environment Agency, Historic England and Natural England as well as HBC for review and comment. Key part of this engagement is to understand if we will be expected to undertake an Strategic Environmental assessment. If yes this will add about 3 months to our program of work.

If we don't have to do an SEA we should plan to undertake a Sustainability Appraisal. David Gluck will help with this. In addition we will need to produce a Consultation Appraisal document plus a Condition Statement. Again David Gluck will help us with these.

Harrogate will tell us if we need to do an SEA.

Public Consultation.

Look to start early march 2017 unless we need to do SEA.

Consultancy period 6 weeks.

- High profile approach to driving public enagement.

- Market stall

- Banner on high street

- Pup up signs

- Publicity social media,

- Mailing to every house publicising consultancy and providing an executive summary of doc. Doc size likely to be 8 pages.

- Pop up shop

- Presence at sporting events

- Presence in parks at weekends

- Attend community events

- NDP branding build on what we have rather than start again.

Document Development

There is a new master document. This is version sent to statutory agencies. Only section missing is policy maps. HBC have offered to produce policy maps for us for inclusion in final doc.  DG and DG to meet with HBC to discuss next steps.

Issues to pick up as document develops – may need new policy statements.

- Protection of playing fields

- Protection of Tourist Accommodation.

- Consider possibility of attracting town centre hotel plus do more to promote bed an breakfast accommodation.

Budget

Team undertook review of draft budget for 2017/18. DG will submit to KTC for consideration.

Next meeting 10th Jan – Council Committee Room