Knaresborough Neighbourhood Development Working Group

Meeting Minutes 28th Feb 7:30 pm   Committee Room, Knaresborough House, Knaresborough, HG5 0HW

Meeting Minutes

Attending

David Goode (chair), Mavis Clemmitt, Wendy Sanderson, David Gluck, Shaun Oaks.

Apologies

Bryan Robinson, Christine Willoughby, Andrew Willoughby, Bill Rigby, Emma Walsh, Andy Grinter, David Bulmer

Mins from meeting 10th Jan. approved.

Pre-Consultation Engagement – responses received from HBC, Historic and Natural England and Environment agency.

Issue with Natural England requesting a Strategic Environmnetal Assesment. Reviewed with HBC they feel we don’t need to do one and will take issue up with Natural England on our behalf.

Policy Maps - HBC have agreed to do these for us. All our maps have been passed on to HBC.

Manse Farm update following KTC meeting with developer. Still in negotiation with builders. Expect to make submission to HBC on reserved mater in the summer with a potential stat date for building in the Autumn.

Document and consultancy activities to start April 17 to completion of the NDP program.

- Sustainability Appraisal

- Consultancy statement

- Basic Condition Statement

- Parallel activity update Master Doc to product Reg 14 version to be used in public consultation.

- 6-week public consultancy

- Produce Consultancy Report based on consultation responses

- Amend Master Doc to reflect outcome of consultation

- Submit Reg 16 doc to HBC for their review.

- Submit to examiner

- Referendum

AOB

Next meeting date to be agreed at this meeting 5th April.