Knaresborough Neighbourhood Development Working Group

Meeting Munities 5th April 7:30 pm   Council Chamber, Knaresborough House, Knaresborough, HG5 0HW

Meeting Attendees

David Gluck, David Goode, Mavis Clemmitt, Brian Robinson, Bill Rigby

Apologies

Andrew and Christine Willoughby, Andy Grinter, David Bulmer, Emma Walsh

Mins of 28th Feb approved

Pre-Consultation Engagement Update – HBC still sorting out issues with Natural England Response – HBC officer been on holiday going to follow up again on return.

Policy Maps Update – HBC officer undertaking this work going to retire HBC still committed to complete task but will be delayed as new officer takes up this responsibility.

Next steps – Complete next version of master document. Master has been updated to reflect HBC feedback. Now needs final read through. Documents now needing development was discussed

1. Sustainability Appraisal - consultant will complete this document

2. Consultation Statement – steering group needs to won completing this document.

3. Basic Conditions Statement - consultant will complete this document.

There is cross over in terms of content development between docs1. and 3. Document needs to consider alignment of our policies with NPPF, Local Plan, Environment, Human Rights, Community, Society and Economy.

To start development of Reg 14 Consultancy document it was agreed that team would run a workshop at next meeting to collectively record all the consultancy work that has been undertaken since the start of the program.

Document needs to capture history – what, when, how, why – needs to demonstrate how plan developed based on consultancy work. David Gluck will provide template for this.

Reg 14 document will need to list out all comments from consultancy of final document.

Community Engagement Town Meeting – Emma Walsh did a great job of presenting our NDP program to attendees of KTC Annual Town Meeting. Our thanks to Emma for this.

Public Consultation Planning – we need to start to create list of sake holders that we need to consult with.

Next meeting date 10th May Council Camber if available.